## E-healthcare (2022-12-09 16_17_
WBS # | Name / Title | Type | Start Date | End Date | Percent Complete
1 | Project Timeline | project | 2022-11-15 | 2023-01-04
1.1 |  | group | 2022-11-15 | 2022-11-25 | 100
| Team Making | task
| Collection of data | task
1.2 |  | group | 2022-11-26 | 2022-12-06 | 100
| Data Analyzing | task
| Data Cleaning and Imputation | task
| Forming the Research Question | task
| Data Exploration | task
| Data Visulization of the result | task
1.3 |  | group | 2022-12-01 | 2022-12-17 | 79.63
| Applying Linear Regression Model | task
| Visualization of the Linear Regression Model | task
| Applying RandomForest Model | task
| Visualization of the RandomForest Model | task
| Applying DecisionTree Model | task
| Visualization of the DecisionTree Model | task
| Applying Gradient Boosting Regression | task
| Visualization of the Gradient Boosting Regression | task
| Result Analysis | task
| Comparative Analysis | task
| Testing the Model | task
1.4 | WalkThrough and Report | group | 2022-12-18 | 2023-01-04 | 0
| Draft Report | task
| Final Report | task
| Presentation Slides | task