## GanttChart
Predicting GDP
| Project Start Date | 2022-11-15 |  |  |  | Display Week | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
[8 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12 | [6 empty] | 2022-12-19 | [6 empty] | 2022-12-26 | [6 empty] | 2023-01-02
 | time axis 2022-11-14 to 2023-01-08
WBS | TASK |  | PREDECESSOR | START | END | DAYS | % DONE | time axis 2022-11-14 to 2023-01-08
1 | Data Collection and Processing |  |  |  | -
1.1 | Reviewing Online Literature |  |  | 2022-11-15 | 2022-11-25 | 11 | 100%
1.2 | Team Making |  |  | 2022-11-15 | 2022-11-18 | 4 | 100%
1.3 | Data Collection from source |  |  | 2022-11-15 | 2022-11-18 | 4 | 100%
1.4 | Understanding the Data |  |  | 2022-11-18 | 2022-11-20 | 3 | 100%
1.5 | Finalization of Data |  |  | 2022-11-25 | 2022-11-25 | 1 | 100%
1.6 | Understanding Libraries |  |  | 2022-11-26 | 2022-11-27 | 2 | 100%
1.7 | Data Cleaning |  |  | 2022-11-27 | 2022-11-29 | 3 | 100%
1.8 | Understanding Hadoop |  |  | 2022-11-27 | 2022-11-29 | 3 | 100%
1.9 | Understanding Pyspark |  |  | 2022-11-30 | 2022-12-01 | 2 | 100%
1.10 | Making Decisions on using Python tools |  |  | 2022-12-01 | 2022-12-03 | 3 | 100%
1.11 | Describing the Data |  |  | 2022-12-01 | 2022-12-03 | 3 | 100%
1.12 | Finding the Correlation |  |  | 2022-12-05 | 2022-12-06 | 2 | 100%
1.13 | Big Data Hypothesis |  |  | 2022-12-05 | 2022-12-06 | 2 | 100%
2 | Model building |  |  |  | -
2.1 | Linear Regression |  |  | 2022-11-15 | 2022-11-17 | 3 | 100%
2.2 | Random Forest Regression |  |  | 2022-12-03 | 2022-12-06 | 4 | 100%
2.3 | Gradient Boosting Regression |  |  | 2022-12-07 | 2022-12-15 | 9 | 100%
2.4 | Decision Tree Regression |  |  | 2022-12-07 | 2022-12-15 | 9 | 100%
2.5 | Comparative Analysis |  |  | Fri 12/07/2022 | Fri 12/07/22 | 1 | 100%
2.6 | Testing |  |  | 2022-12-17 | 2022-12-17 | 1 | 100%
3 | Report and Walkthrough |  |  |  | -
3.1 | Draft Report |  |  | 2022-12-18 | 2022-12-20 | 3 | 100%
3.2 | Final Report |  |  | 2022-12-20 | 2022-12-30 | 11 | 100%
3.3 | Video Walkthrough / Presentation |  |  | 2022-12-25 | 2023-01-01 | 8 | 100%
3.4 | Editing and Cleanup |  |  | 2023-01-01 | 2023-01-04 | 4 | 100%
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.